## Overview
Azure / DevOps Learning Tracker
Active apps | One shared React SPA + three small FastAPI APIs: Chat, Document Q&A, approval-gated Agent
Active window | Sep 26-27 2026, 16-hour accelerated sprint; destroy by Sep 27 20:00 IST
Credit evidence | INR 19,109.25 remaining; portal displays Sep 28 expiry; do not rely on Sep 28
Sprint budget | Expected <INR 500; hard cap INR 1,500; see 'GenAI Sprint' tab
Golden rule | A day is Done only when Destroyed? = Yes (except keep-listed items)
Your role | Portal clicks, az commands, terraform plan review + apply, verification
Agent's job | TF files + exact commands prepared before each session; docs updated
Docs | Start: AZURE_GENAI_BEGINNER_HANDBOOK.md/html/docx · 1) solution overview · 2) deployment guide · 3) journal
Paused curriculum | The original 28-day plan remains for later; VM and AKS stages are paused
Cost tabs | 'GenAI Sprint' tracks the active blocks; legacy Day Cost Plan is retained; Cost Log records actuals

## GenAI Sprint
Block | Sprint day | Outcome | Azure services | Cost guardrail | Status | Evidence | Destroyed?
1 | Day A | Expiry, budget, subscription, quotas, providers | Cost Management, Resource Providers | ₹0 | Not started
2 | Day A | Three flows + local shared React SPA and FastAPI contracts + shared cloud platform | React, FastAPI, RG, Foundry, ACR, Key Vault, Monitor | <₹100 target | In progress | Local App 1 React/FastAPI contract implemented: MISS→HIT, zero hit tokens, TTL, scoped keys, and 20-request stampede test verified. Shared Azure platform pending. | -
3 | Day A | App 1 FastAPI on Fargate-equivalent hosting + React Chat page | Container Apps, Static Web Apps, ACR | free-quota target | Not started
4 | Day A | Cache MISS→HIT, managed identity, APIM, trusted HTTPS certificate | Azure Managed Redis, RBAC, APIM | Redis estimate required | Not started
5 | Day A | Concurrent users, autoscaling, stampede lock, break/fix, revision rollback | Container Apps, Redis, App Insights | <₹100 target | Not started
6 | Day A | Repeat App 1 deployment from learner's saved commands | ACR, Container Apps, APIM | <₹50 target | Not started
7 | Day A | Blob, AI Search, Content Safety, lexical/vector retrieval | Storage, AI Search Free, Content Safety F0 | <₹100 target | Not started
8 | Day A | App 2 FastAPI + React Document Q&A; grounded and unknown answers | Container Apps, Static Web Apps, Foundry, AI Search | <₹100 target | Not started
9 | Day B | Durable runtime, queue TTL/dead letter, Cosmos item TTL | Functions, Storage, Service Bus, Cosmos DB | free-quota target | Not started
10 | Day B | App 3 FastAPI + React Agent page + approval orchestrator + worker | Container Apps, Static Web Apps, Durable Functions | <₹100 target | Not started
11 | Day B | Concurrent runs: approve, reject, approval timeout, queue depth | Durable Functions, Service Bus, Cosmos DB | <₹50 target | Not started
12 | Day B | Duplicate/changed approval, message expiry, retry, dead letter, replay, lock renewal | Service Bus, Durable Functions, App Insights | <₹50 target | Not started
13 | Day B | Three APIM routes, HTTPS-only, certificate inspection, rate limits | APIM Consumption, managed TLS | near ₹0 | Not started
14 | Day B | OIDC build/publish/deploy immutable revision | GitHub Actions, ACR, Container Apps | <₹50 target | Not started
15 | Day B | Cross-app logs, tiny load tests, alert, independent repeat deployment | Azure Monitor, Container Apps revisions | <₹100 target | Not started
16 | Day B | Evidence, actual cost, delete and prove absence | Cost Management, Resource Group | ₹0 | Not started
Deadline | Delete sprint RG and verify absence by Sep 27 20:00 IST
Hard cap | INR 1,500; stop before any unexpected paid tier

## Free Quotas
Category | Service | Period | Included amount | Sprint decision
AI/RAG | Azure AI Search | Always | 50 MB; 10,000 documents; 3 indexes | Core: Free SKU
Hosting | Container Apps Consumption | Always | 180,000 vCPU-s; 360,000 GiB-s; 2M requests/month | Core: scale to zero
Hosting | Static Web Apps Free | Free tier | Hosting quota shown by the selected plan | Core shared React SPA
Gateway | API Management Consumption | Monthly included | First 1M API operations/subscription/month | Core
Safety | Content Safety F0 | Free tier | 5,000 text records + 5,000 images/month; hard stop | Core
Registry | Container Registry Standard | 12 months | 1 registry; 100 GB; 10 webhooks | Core: exact Standard SKU
Data | Blob Storage Hot LRS | 12 months | 5 GB; 20,000 reads; 10,000 writes | Core
Security | Key Vault Standard | 12 months | 10,000 RSA-2048 key or secret operations | Core
Document AI | Document Intelligence S0 | 12 months | 500 pages | Stretch
NLP | Azure Language | Always | 5,000 text records | Stretch
Compute | Functions Consumption | Monthly grant | 1M executions + 400,000 GB-s | Core durable workflow
Events | Event Grid | Always | 100,000 operations/month | Stretch Blob trigger
Messaging | Service Bus Standard | 12 months | 750 hours + 13M operations | Core async queue
Database | Cosmos DB free tier | Always | 1,000 RU/s + 25 GB when free tier selected | Core status/audit
Cache | Azure Managed Redis | Paid | No verified free-account grant; hourly SKU charge | One block if estimate fits; local fallback
Database | PostgreSQL Flexible B1ms | 12 months | 750 hours + 32 GB data + 32 GB backup | Defer
Compute | Eligible Linux/Windows VMs | 12 months | 750 hours each for listed B1s/B2pts v2/B2ats v2 | Defer
AI platform | Microsoft Foundry | Platform free | Consumed features bill at their own rates | Core
Model | Foundry/OpenAI inference | Paid | No general free-token grant; model/token rates | Core: strict limits
Observability | Azure Monitor / Log Analytics | Paid ingestion | Platform metrics/activity logs have free units; log ingestion metered | Core: sample/cap
Important | Quotas reset monthly and do not roll over. Exact SKU and the subscription's Cost Management > Free services grid are authoritative. PAYG overages bill the card.
Official list | https://azure.microsoft.com/en-us/pricing/free-services/

## Daily Plan
Day | Date | Dow | Phase | Goal | Azure services | Portal steps | CLI commands (key) | Time | Status | Cost est. $ | Destroyed? | Notes
1 | 2026-08-31 | Mon | Setup | Repo governance + OIDC prep + first local run | none | Branch protection on main; GHCR packages public; Entra app + federated credential; Contributor role | az login; az account list; docker compose up --build (local) | 1h | Done | 0 | Yes | GitHub governance, public GHCR, Entra OIDC/RBAC, and local five-container flow completed. Fixed missing nginx /api proxy. Containers and pgdata volume destroyed.
2 | 2026-09-01 | Tue | Foundations | Azure anatomy: subscription, RGs, providers | Resource Groups | Subscriptions, Resource groups, Cost Management blades | az login; az account set; az group create/delete; az resource list | 1h | In progress | 0 |  | Accelerated two-day GenAI sprint started after portal confirmed INR 19,109.25 credit expires Sep 28. Use ephemeral Cloud Shell; destroy by Sep 27 20:00 IST.
3 | 2026-09-02 | Wed | Secrets | Key Vault manually in the portal | Key Vault, RBAC | Create vault (RBAC); Secrets tab add LLM-PROVIDER; IAM role assignment | az keyvault show; az keyvault secret set/show | 1h | Not started | 0.01
4 | 2026-09-03 | Thu | Secrets | CLI-driven vault access with least privilege | Key Vault, Entra ID | Role assignments blade on the vault | az ad sp create; az role assignment create; az keyvault secret show | 1h | Not started | 0.01
5 | 2026-09-04 | Fri | IaC | Terraform 101: resource group via code; state concept | Terraform (azurerm) | Verify TF-created RG in portal; read the plan output line by line | terraform init; plan -out; apply; state list; destroy | 1h | Not started | 0
6 | 2026-09-05 | Sat | IaC | Key Vault + secret entirely in Terraform | Key Vault via TF | Compare portal form fields with TF resource attributes | terraform apply; terraform destroy | 1h | Not started | 0.01
7 | 2026-09-05 | Sat | Integration | App reads config from Key Vault; OIDC app ready for GitHub | Key Vault, Entra federated credential | Federated credential subject: repo:jnaveen-ds/Testing_end_to_end:ref:refs/heads/main | az keyvault secret show; verify app /health uses vault config | 1h | Not started | 0.01
8 | 2026-09-06 | Sun | Cleanup | Week 1 review + cost check | Cost Management | Cost analysis blade; budget review | az group list; az consumption usage list | 30m | Not started | 0
9 | 2026-09-07 | Mon | Week 2 · VM | Terraform: Linux VM + VNet + subnet + NSG + public IP | Linux VM, VNet, NSG, disk, public IP | VM blade: boot diagnostics, NSG rules, size/cost estimate | terraform apply (infra/day9); az vm list; ssh | 1h | Not started | 1.2
10 | 2026-09-08 | Tue | VM | Deploy the app stack onto the VM; open only needed ports | VM, Docker Compose, NSG rules | NSG inbound rules audit; boot diagnostics | ssh; docker compose up -d --build; curl /health | 90m | Not started | 1.2
11 | 2026-09-09 | Wed | VM | TLS + reverse proxy in front of the app | nginx, TLS (certbot) | Certificates; custom domain (if any) | nginx config; certbot --nginx or openssl self-signed | 1h | Not started | 1.2
12 | 2026-09-11 | Fri | CD | Actions deploys to the VM: SSH + pull sha-tagged image + restart | GitHub Actions, VM | GitHub environment secrets review (never in git) | git push -> deploy job -> curl public /health | 1h | Not started | 1.3
13 | 2026-09-12 | Sat | Chaos | Break things on purpose: kill worker, wrong env, full disk; recover | ops skills | Serial console; boot diagnostics | systemctl; docker; df -h; journalctl | 90m | Not started | 1.2
14 | 2026-09-13 | Sun | Cleanup | Destroy the VM resource group; review week-2 spend | Cost Management | Cost analysis | az group delete; terraform destroy | 30m | Not started | 0
15 | 2026-09-14 | Mon | Week 3 · Containers | Log Analytics + Container Apps environment + deploy API | Log Analytics, Container Apps | Container app blade: Revisions, Log stream, Scale | az containerapp env create; TF apply (infra/day15) | 90m | Not started | 0.05
16 | 2026-09-15 | Tue | Containers | Worker as second app; scale-to-zero via KEDA rule | Container Apps scale rules (KEDA) | Scale tab: min 0 / max 3; watch 0->1 on submit | az containerapp update --min-replicas 0 | 1h | Not started | 0.05
17 | 2026-09-16 | Wed | Data | Azure PostgreSQL Flexible (B1ms) wired via Key Vault secret | PostgreSQL Flexible, Key Vault | Server networking + metrics blades; firewall rules | TF apply; az keyvault secret set (connection string) | 90m | Not started | 0
18 | 2026-09-17 | Thu | Autoscaling | Load test with hey; watch replicas scale in the Metrics blade | Container Apps autoscale, Metrics | Metrics blade: replica count vs request rate | hey -c 20 -z 2m https://<app-url> | 1h | Not started | 0.5
19 | 2026-09-19 | Sat | Website | WEBSITE DEPLOYMENT: React UI on Azure Static Web Apps (free tier), pointed at the API | Static Web Apps (+ optional custom domain) | SWA portal: environments, tokens, custom domain | az staticwebapp create; swa deploy; verify site + API wiring | 90m | Not started | 0
20 | 2026-09-20 | Sun | Resilience | Rollback drills: bad revision -> revert; traffic split blue/green | Container Apps revisions | Revision management + traffic weighting UI | az containerapp revision list/activate; ingress traffic set | 1h | Not started | 0.05
21 | 2026-09-20 | Sun | Cleanup | Destroy week-3 compute; keep only free-tier DB + images | - | Cost check | az group delete (each learn RG) | 30m | Not started | 0
22 | 2026-09-22 | Tue | Kubernetes | AKS evening: 1-node free-tier cluster; deploy API+worker; DESTROY tonight | AKS, kubectl, Azure Load Balancer | AKS blade: workloads, services, logs | az aks create; get-credentials; kubectl apply/get; az aks delete | 2h | Not started | 1
23 | 2026-09-23 | Wed | Config | App Configuration + feature flag; change behavior without redeploy | App Configuration | Feature manager UI | az appconfig create; az appconfig kv set; wire app endpoint | 1h | Not started | 0.01
24 | 2026-09-24 | Thu | Resilience | App Insights live; kill DB mid-traffic; alert on error rate | Application Insights, Monitor alerts | Live Metrics; Log Analytics queries; create alert rule | az monitor metrics alert create | 90m | Not started | 0.05
25 | 2026-09-25 | Fri | Pipeline | Full automated flow: PR -> CI -> publish -> deploy staging -> approval -> prod -> rollback | OIDC deploys, environments, approvals | GitHub environment protection rules | watch the Actions run end to end | 90m | Not started | 0.05
26 | 2026-09-26 | Sat | FinOps | Sweep + destroy everything not deliberately kept; review spend | Cost Management | Cost analysis vs budget; verify alerts fired | az group list; az group delete per learn-* RG | 90m | Not started | 0
27 | 2026-09-27 | Sun | Portfolio | Screenshot dashboards -> docs/PORTFOLIO.md -> destroy the rest | - | Screenshot everything first | final az group delete | 1h | Not started | 0.41

## Day Cost Plan
Day | Date | Services billed that day | Meter / rate (approx list price) | Usage | Est. cost $ | Cumulative $ | Free-tier status
1 | 2026-08-31 | none (local only) | - | - | 0 | 0
2 | 2026-09-01 | Resource groups (empty) | RGs are free; only contents bill | - | 0 | 0
3 | 2026-09-02 | Key Vault | $0.03 per 10,000 operations | tiny | 0.01 | 0.01 | Operations meter only — effectively free
4 | 2026-09-03 | Key Vault | $0.03 per 10,000 operations | tiny | 0.01 | 0.02 | Operations meter only — effectively free
5 | 2026-09-04 | Resource group via Terraform | state kept in local file, $0 | - | 0 | 0.02
6 | 2026-09-05 | Key Vault via Terraform | $0.03 per 10,000 operations | tiny | 0.01 | 0.03 | Operations meter only — effectively free
7 | 2026-09-05 | Key Vault + Entra app | app registration free | - | 0.01 | 0.04 | Operations meter only — effectively free
8 | 2026-09-06 | cleanup day (nothing running) | - | - | 0 | 0.04
9 | 2026-09-07 | VM B2s (24h) + public IP + 30GB disk | ~$1.00 compute + $0.09 IP + $0.10 disk | 24h | 1.2 | 1.24
10 | 2026-09-08 | VM day 2 (compose stack + image build) | same meters | 24h | 1.2 | 2.44
11 | 2026-09-09 | VM day 3 (TLS / nginx) | same meters | 24h | 1.2 | 3.64
12 | 2026-09-11 | VM day 4 (CI deploys hitting it) | compute + egress ~$0.05 | 24h | 1.3 | 4.94
13 | 2026-09-12 | VM day 5 (chaos tests) | same meters | 24h | 1.2 | 6.14
14 | 2026-09-13 | VM destroyed the evening before | resource group deleted | 0h | 0 | 6.14
15 | 2026-09-14 | Container Apps env + API app (mostly idle) | ~$0.000024/vCPU-s consumption | minutes | 0.05 | 6.19
16 | 2026-09-15 | API + worker, brief scale-up tests | consumption plan, 2M requests free | minutes | 0.05 | 6.24
17 | 2026-09-16 | PostgreSQL B1ms + apps | free tier: 750 B1ms hours + 32GB/mo | hours | 0 | 6.24 | 12-month free allowance covers it
18 | 2026-09-17 | Load test: replicas briefly at 2-3 | consumption plan | 1-2 h | 0.5 | 6.74
19 | 2026-09-19 | Static Web Apps free tier + egress | free tier, ~100GB bandwidth/month free | 1 day | 0 | 6.74 | Free tier (no charge)
20 | 2026-09-20 | Revision/rollback drills on existing apps | no new meters | - | 0.05 | 6.79
21 | 2026-09-20 | everything destroyed | - | - | 0 | 6.79
22 | 2026-09-22 | AKS evening: 1 node B2ms ~8h + LB | ~$0.083/hr node + ~$0.01/hr LB | 8h | 1 | 7.79 | Control plane free; you pay the node
23 | 2026-09-23 | App Configuration | free tier: 1k requests/day | tiny | 0.01 | 7.8 | Free tier
24 | 2026-09-24 | App Insights + Log Analytics | log ingestion metered; platform metrics free | tiny | 0.05 | 7.85 | Log ingestion is metered; keep volume tiny
25 | 2026-09-25 | pipeline reruns on existing resources | no new meters | - | 0.05 | 7.9
26 | 2026-09-26 | finops sweep (nothing new) | - | - | 0 | 7.9
27 | 2026-09-27 | write-up day (DB kept only if free tier) | B1ms beyond allowance = ~$0.41/day | - | 0.41 | 8.31
[5 empty] | PLANNED TOTAL | 8.31
Without free-account allowances the same month would cost roughly $40-70 (Postgres ~$12/mo + SWA Standard + App Insights + more VM/AKS hours).

## Deployments
# | Deployment | Azure services | Day | End-state plan | Status | Evidence link
1 | Local compose stack (5 containers) | Docker Compose | Day 1 | destroyed after verification | Done | docs/LEARNING_JOURNAL.md#day-1--github-governance-azure-oidc-and-first-local-run
2 | Shared website: React SPA with Chat, Document Q&A, and Agent pages | Azure Static Web Apps | Sprint Day A | destroy Sep 27 | Not started
3 | Chat FastAPI: Fargate-equivalent service with cache and TLS | Container Apps, ACR, Managed Redis, APIM | Sprint Day A | Redis same-block; rest Sep 27 | Not started
4 | Document Q&A FastAPI: cited RAG | Container Apps, Blob, AI Search, Foundry | Sprint Day A | destroy Sep 27 | Not started
5 | Approval-gated Agent FastAPI: durable wait, queue, status | Durable Functions, Service Bus, Cosmos DB | Sprint Day B | destroy Sep 27 | Not started
6 | Immutable OIDC redeploy and rollback | GitHub Actions, ACR, Container Apps | Sprint Day B | destroy Sep 27 | Not started

## Cost Log
Date | Resource group | Service | Est. cost $ | Actual cost $ | Destroyed? | Notes
2026-08-31 | local (no Azure RG) | GitHub/Entra setup + Docker Compose | 0 | 0 | Yes | Local stack and pgdata volume removed; reusable $0 identity/config retained
TOTAL:

## Destroy Ritual
Run at the END of EVERY session. No exceptions.
1. SCREENSHOT dashboards first (portfolio evidence)
2. az group list -o table -- know exactly what exists
3. az group delete -n learn-<stage>-<date> --yes --no-wait
4. Terraform days: cd infra/<day> && terraform destroy -- review: must list only today's resources
5. az resource list -o table ¦ grep <date> -- no orphaned disks/NICs/IPs
6. az consumption usage list --top 5 -o table -- know today's cost
7. Next morning: az group list -- nothing unexpected alive